## Design Projects List
Item | Project Name | Project Number | Est. Construction Year | Construction NTP Date | Bid Number | Est. Advertise Date | Commission District | Project Status | Cm Firm | County Project Engineer | County Construction Manager | Design Consultant | Design Fund | FY Funds | Contractor Bid Est. | Engineer Bid Estimate | Shape__Length | Design L# | Work Order # | % Complete | Cubbie | Utility Letters | Construction Contract Date | GUS Database | Construction Fund | Finance Name | Bid Name | Design NTP | 30% Submittal | Record of Survey | RW Acquisition Documents | 60% Submittal | 90% Submittal | PreFinal | Final | Actual Advertise Date | What Else? | Comm District
1 | Airport Channel - Naples | FCLA10H | TBD | TBD | TBD | 2020-06-01 | G | Design | TBD | Christine | TBD | Atkins | RFCD | 2018 | 0 | 25000000 | 6179.817 | L2168 | D2014-006 | 90 | 75 | Y |  | 865 | RFCD | Airport Channel - Naples | Airport Channel - Naples | [10 empty] | G
2 | Airport Interchange Phase 3 | B183214 | 2020 | TBD | TBD | 2020-08-01 | A, G | Design | TBD | Spring Dineen | TBD | WSP | MTP | 2019 | 0 | 14200000 | 12110.5753 | L2206 | D2018-013 | Prefinal | 67 | Y |  | 974 | MTP | Airport Interchange Phase 3 | Beltway Airport Interchange Phase III | [10 empty] | A,G
3 | Bellagio Pedestrian Bridge | S16089A | [7 empty] | Spring Dineen |  | GCW, Inc. | [5 empty] | L2458 | D2022-25 | Pre Des | 48 | N | [15 empty] | G
4 | Beltway - CC 215 Beltway Trail Bridge, Charleston | R00190Q | [7 empty] | Kaizad Yazdani |  | GCW, Inc. | [5 empty] | L2375 | D2022-003 | 100 | 66 | N | [15 empty] | C,F
5 | Beltway - CC 215 Sunset/Durango Ramps | BW11323 | [7 empty] | Spring Dineen |  | Jacobs | [5 empty] | L2483 | D2024-014 | 90 | 81 | N | [15 empty] | F,B
6 | Beltway - CC215, Charleston to Far Hills Dr (Phase 1) | BW22209 | [7 empty] | Rahel Shibeshi |  | GCW, Inc. | [5 empty] | L2378 | D2022-006 | 60 | 87 | Y | [15 empty] | C
7 | Beltway - CC215, Summerlin Pkwy to Hualapai Way (Phase 2) | BW22209 | [7 empty] | Rahel Shibeshi |  | GCW, Inc. | [5 empty] | L2325 | D2019-040 | 30 | 82 | N | [15 empty] | C
8 | Beltway - CC 215, Frontage Rd, Decatur to Sunset (Phase 2) | BW19821 |  |  |  |  | A, F | Design |  | Christine | TBD | Atkins | MTP | 2020 |  |  | 72117.1178 | L2404 | D2019-024 | 60 | 51 | N | [15 empty] | A,F
9 | Beltway - CC215, US 95 To Decatur Blvd | BW24101 | [7 empty] | Richard Robinson |  | Horrocks | [5 empty] | L2543 | D2024-034 | 0 | TBD | N | [15 empty] | B
10 | Blue Diamond Railroad Channel (BDW5-0026), Blue Diamond Road to Rainbow Boulevard | FCLA38G | [7 empty] | Richard Robinson |  | GCW, Inc. | [5 empty] | L2313 | D2020-017 | 90 | 72 | Y | [15 empty] | F
11 | Blue Diamond Wash Trail, Durango to Hualapai Trail Connectivity | R00190N | [7 empty] | Spring Dineen |  | Westwood | [5 empty] | L2459 | D2022-12 | 90 | 37 | N | [15 empty] | F
12 | Broadbent Blvd, Wetlands Park Lane to City of Henderson Limits | R006LFT | [7 empty] | Richard Robinson |  | Jacobs | [5 empty] | L2331 | D2021-005 | 60 | 97 | Y | [15 empty] | G
13 | Boulder Hwy/Desert Inn - Lamb Intersection Improvements | N15173A | [7 empty] | Kaizad Yazdani |  | GCW, Inc. | [5 empty] | L2559 | D2024-041 | 0 | - | [16 empty] | E
14 | Broadbent Yard Improvements, Phase I | In House | [7 empty] | Bryan Osborne |  | In House | [5 empty] | L2374 | D2022-001 | 100 | _ | N | [15 empty] | D
15 | Carey Avenue, Pecos Road to Nellis Blvd | R016LFT | [7 empty] | Tim Piparo |  | In House | [5 empty] | L2320 | D2021-001 | 60 | 80 | N | [15 empty] | D
16 | Casino Drive Sedimentation Project/SR 163-Sedimentation Phase 2 | FLAU04A | [7 empty] | Rahel Shibeshi |  | GCW, Inc. | [5 empty] | L2344 | D2021-007 | ADV | 68 | Y | [15 empty] | A
17 | Casino Drive South - Needles Highway to Harrah's Hotel | [8 empty] | Rahel Shibeshi |  | GCW, Inc. | [5 empty] | L2226 | D2019-010 | 30 |  | N | [15 empty] | A
18 | Cimarron Road, Blue Diamond Rd to Pebble Rd (Under Fort Apache Contract) | R217AFT | 2020 | TBD | TBD | 2020-02-01 | F | Design |  | John/Bryan | TBD | In House | FRI | TBD | 0 | 1500000 | 2096.7839 | L2224 | D2019-007 | 30 | 27 | N |  | 991 | TBD | Cimarron Road, Blue Diamond Rd to Pebble Rd | Cimarron Road, Blue Diamond Road to Pebble Road | [10 empty] | F
19 | City of Henderson - Eastern from Serene to Ione Coordination | In House | 2020 | TBD | TBD | 2020-02-01 | F | Design |  | Bryan/Tim | TBD | In House | FRI | TBD | 0 | 1500000 | 2096.7839 | _ | D2022-35 | 90 | 0 | N |  | 991 | TBD | Cimarron Road, Blue Diamond Rd to Pebble Rd | Cimarron Road, Blue Diamond Road to Pebble Road | [10 empty] | A
20 | Cottonwood Avenue Storm Drain - Swapp Dr to Heyer St | In House | [7 empty] | Bryan/Humberto Rivas |  | In House | [5 empty] | L2424 | D2022-36 | 30 | 79 | N | [15 empty] | B
21 | Cottonwood Cove Road, US 95 to Michael Wendell Way (Searchlight Multi Use Trail) | R061JFT B84061H | [7 empty] | Bryan/Jinxin Xie |  | In House | [5 empty] | L2116 | D2015-006 | 100 | 84 | Y | [15 empty] | A
22 | Decatur Blvd, Silverado Ranch to Blue Diamond (Ph2) | In House | 2022 | TBD | TBD | 2020-12-01 | A, F | Design | TBD | Bryan/Bert | TBD | In House | RTC FTI | 2018 | 0 | 19800000 | 21271.0898 | L2453 | D2022-029 | 60 | 63 | N |  | 869 | RTC MVFT | Decatur Boulevard, Cactus Ave to Warm Springs Rd | Decatur Boulevard, Cactus Avenue to Warm Springs Road | [10 empty] | A,F
23 | Decatur Blvd, Blue Diamond to Warm Springs (Ph3) | In House | 2022 | TBD | TBD | 2020-12-01 | A, F | Design | TBD | Bryan/Ulises | TBD | In House | RTC FTI | 2018 | 0 | 19800000 | 21271.0898 | L2454 | D2022-029 | 60 | 63 | N |  | 869 | RTC MVFT | Decatur Boulevard, Cactus Ave to Warm Springs Rd | Decatur Boulevard, Cactus Avenue to Warm Springs Road | [10 empty] | A,F
24 | Desert Inn Rd - Cimarron Rd to Decatur Blvd | MRD0001 | [7 empty] | Bryan/An |  | In House | [5 empty] | L2501 | D2024-016 | 30 |  | N | [15 empty] | F
25 | Duck Creek/ Blue Diamond, Bermuda to Las Vegas Blvd | FCLA39A | 2021 | TBD | TBD | 2020-09-01 | A | Design | TBD | Richard Robinson | TBD | Stantec Consulting | RFCD | 2021 | 0 | 7500000 | 5451.4882 | L2381 | D2019-017 | 90 | 25 | Y |  | 1015 | TBD | Duck Creek/Blue Diamond, Bermuda to Las Vegas Blvd | Duck Creek/Blue Diamond, Bermuda to Las Vegas Blvd | [10 empty] | A
26 | Flamingo Wash, UPRR to Hotel Rio Drive | FCLA10F | [7 empty] | Richard Robinson |  | WSP | [5 empty] | L2348 | D2021-016 | 60 | 53 | N | [15 empty] | E,F
27 | Flamingo Wash - Cimarron Branch, Russell Road to Patrick Lane | FCLA01F | 2021 | TBD | TBD | 2020-06-01 | E | Design | TBD | GCW/ Rahel | TBD | Atkins | RFCD | 2019 | 0 | 5068800 | 2540.6378 | L2383 | D2022-009 | 90 | 22 | N |  | 1012 | TBD | Flamingo Wash, Maryland Pkwy and Palos Verde St | Flamingo Wash, Maryland Parkway to Palos Verdes Street | [10 empty] | A,E
28 | Flamingo Wash - Grand Canyon Diversion Structure | LAD0324 | [7 empty] | Bryan/Joe |  | In House | [5 empty] | L2408 | D2022-028 | 30 |  | N | [15 empty] | F
29 | Grand Canyon Drive Bus Turnout at Rochelle Ave (includes Pedestrian Flasher) | R239FFT | 2020 | TBD | TBD | 2020-03-01 | G | Design | TBD | Tim/Rex | TBD | In House | MTP Resort | 2012 | 0 | 2386470 | 2764.6993 | L2435 | D2023-002 | 100 | 63 | N |  | 782 | MTP Resort | Harmon Avenue, Arville to Swenson (Audrie to Koval) | Harmon Avenue, Audrie to Koval: Widening | [10 empty] | G
30 | Green Tree and Tahoe Culvert Rehabilitation on Vegas Valley Drive | [8 empty] | Bryan/Jinxin Xie |  | In House | [5 empty] | L2502 | D2024-012 | 90 | 90 | Y | [15 empty] | E
31 | Harmon Avenue, Audrie St to La Mar Cir | S003203 | 2020 | TBD | TBD | 2020-03-01 | G | Design | TBD | Tim/Wendy | TBD | In House | MTP Resort | 2012 | 0 | 2386470 | 2764.6993 | L2395 | D2015-022 | 60 | 61 | N |  | 782 | MTP Resort | Harmon Avenue, Arville to Swenson (Audrie to Koval) | Harmon Avenue, Audrie to Koval: Widening | [10 empty] | G
32 | Hollywood Blvd Extension Phase 2, Vegas Valley Drive to Galleria Drive | BW21520 | [7 empty] | Spring Dineen |  | WSP | [5 empty] | L2318 | D2020-12 | 60 | 70 | N | [15 empty] | E,G
33 | Hollywood Boulevard, Lake Mead Boulevard to Cheyenne Avenue | R099DFT | [7 empty] | Richard Robinson |  | Kimley-Horn KHA | [5 empty] | L2283 | D2020-003 | 100 | 69 | Y | [15 empty] | B
34 | James Regional Sports Park | [8 empty] | Kaizad Yazdani |  | GCW, Inc. | [5 empty] | L2474 | D2023-16 | 100 | _ | N | [15 empty] | A
35 | Koval Lane Widening, Tropicana Avenue to Sands Avenue | S160824 S160121 | [7 empty] | Spring Dineen |  | WSP | [5 empty] | L2243 | D2016-018 | 60 | 19 | N | [15 empty] | E,G
36 | Las Vegas Boulevard Roadway Improvements - Russell Rd to Tropicana Ave (Phase C&D) | S190103 | [7 empty] | Kaizad Yazdani |  | GCW, Inc. | [5 empty] | L2490 | D2023-028 | ADV |  | Y | [15 empty] | A,G
37 | Las Vegas Boulevard Roadway Improvements - Flamingo Rd to Spring Mountain Rd (Phase G) | S190103 | [7 empty] | Kaizad Yazdani |  | GCW, Inc. | [5 empty] | L2526 | D2024-036 | 30 | [17 empty] | E,G
38 | Las Vegas Wash and Flamingo Wash Maintenance Access Improvements | MDD0001 | [7 empty] | Bryan/Shawn |  | In House | [5 empty] | L2498 | D2024-007 | 60 | [17 empty] | E
39 | Laughlin Lagoon | SID162B | [7 empty] | Rahel/Kaizad |  | VTN Nevada | [5 empty] | L2188 | D2017-007 | 60 | _ | N/A | [15 empty] | A
40 | Legacy Trail Parking Lot (Various Roadway Rehab WO 11) | N/A | [7 empty] | Kaizad Yazdani |  | GCW, Inc. | [5 empty] | L2426 | D2016-15 | ADV | _ | N | [15 empty] | F
41 | Logandale Trails Access Road | B840212 | [7 empty] | Tim Piparo |  | FHWA | [5 empty] | N/A | D2019-016 | OPENED | 92 | N | [15 empty] | B
42 | Mojave Rd, Fremont St to Charleston Blvd | N15173A |  |  |  |  | E | Design |  | Tim/Rex |  | In House |  |  |  | 0 | 3313.0675 | L2281 | D2020-001 | 90 | 93 | Y |  |  |  |  | Mojave Rd, Freemont St to Charleston Blvd | [10 empty] | E
43 | Monson Channel Improvements, Nellis Blvd to Jimmy Durante Blvd (Various) | FCLA40A | 2021 | TBD | TBD | 2020-07-02 | E, G | Design | TBD | Christine | TBD | CH2M Hill | RFCD Maintenance | 2015 | 0 | 7000000 | 3917.922 | L2221 | D2019-002 | 90 | 38 | Y | [15 empty] | E,G
44 | Mountain Vista Storm Drain | LAD0519 | 2020 | TBD | TBD |  | E | Design | TBD | Bryan/ Rahel Shibeshi | TBD | In House | County LAD | 2015 |  | 2300000 | 5105.814 | L2209 | D2018-020 | 90 (HOLD) | 73 | N |  | 831 | County LAD | Mountain Vista Storm Drain | Mountain Vista Storm Drain | [10 empty] | E,G
45 | Northfork Drainage Channel Ramp | MDD0001 | [7 empty] | Bryan/Joe |  | In House | [5 empty] | L2495 | D2024-005 | 100 |  | N | [15 empty] | A
46 | Orchard Collector, Charleston Blvd to Linden Ave | F000714 | 2021 | TBD | TBD | 2020-06-01 | E | Design | TBD | Richard Robinson | TBD | WSP | RFCD NLV | 2016 | 0 | 4100000 | 4764.0622 | L1647 | D2009-19 | 90 | 14 | N |  | 690 | RFCD NLV | Orchard Detention Basin (Collector, Charleston to Linden) | Orchard Collector, Charleston to Linden | [10 empty] | G
47 | Paradise Road, Harmon to Twain Ave (Phase 3B - Harmon to Sands) | S013201 | 2021 | TBD | TBD | 2020-06-01 | E, G | Design | TBD | Kaizad Yazdani | TBD | Louis Berger WSP | MTP Resort | 2014 | 0 | 11900000 | 4936.4962 | L1711 | D2008-054 | 90 | 65 | Y |  | 783 | MTP Resort | Paradise Road, Harmon Avenue to Desert Inn Road (PH IIIB Harmon Ave to Twain Avenue) | Paradise Road, Harmon Avenue to Twain Avenue | [10 empty] | E,G
48 | Patrick Ln, Durango to Rainbow | P_REHAB | 2020 | TBD | TBD | 2020-07-15 | E, G | Design | TBD | Tim Piparo | TBD | In House | MTP | 2019 | 0 | 10000000 | 5608.0713 | L2455 | D2023-007 | 90 | 11 | Y |  | 1000 | TBD | Bridge Rehab at Harmon, Flamingo, & Spring Mountain | Las Vegas Blvd Pedestrian Bridge Rehabilitation | [10 empty] | E,G
49 | Ped Bridge Rehab on Las Vegas Boulevard at Spring Mountain Rd, Flamingo Rd, Harmon Ave | S200609 | 2020 | TBD | TBD | 2020-07-15 | E, G | Design | TBD | Spring Dineen | TBD | Atkins | MTP | 2019 | 0 | 10000000 | 5608.0713 | L2263 | D2019-004 | 90 | 42 | Y |  | 1000 | TBD | Bridge Rehab at Harmon, Flamingo, & Spring Mountain | Las Vegas Blvd Pedestrian Bridge Rehabilitation | [10 empty] | E,G
50 | Pyle Avenue and Pollock Drive, Starr Avenue and Dean Martin Drive, Starr Avenue and Gilespie Street Traffic Signal Improvements | [8 empty] | Bryan Osborne |  | Kleinfelder/ Lochsa | [5 empty] | L2515 | D2020-022 | 90 | - | Y | [15 empty] | A,F
51 | Rainbow Blvd and CC215 RCB Connection | [8 empty] | Tim Piparo |  | In House | [5 empty] | L2546 | D2024-035 | 30 |  | N | [15 empty] | A
52 | Rainbow Boulevard, Blue Diamond Road to CC 215 Beltway | R010PFT | [7 empty] | GCW/ Rahel |  | Horrocks | [5 empty] | L2324 | D2021-002 | 100 | 4 | Y | [15 empty] | F
53 | Red Rock Legacy Trails | R190RFT | [7 empty] | Richard Robinson |  | FHWA | [5 empty] | L2523 | D2024-020 | Varies | 60 | N | [15 empty] | F
54 | Residential Streets Pavement Reconstruction No. 105 | P_REHAB | [7 empty] | Tim/Dann |  | In House | [5 empty] | L2460 | D2022-027 | OPENED | 78 | Y | [15 empty] | A,D,E
55 | Sandhill Road, Desert Inn Road to Sunset | R083BFT | [7 empty] | Tim Piparo |  | In House | [5 empty] | L2327 | D2021-004 | 60 | 80 | N | [15 empty] | E,G
56 | Sandy Valley - Columbia Pass | R00120A | 2020 | TBD | TBD | 2020-03-01 | F | Design | TBD | Rahel/Kaizad | TBD | GCW, Inc. | RTC DD | 2010 | 0 | 945840 | 51499.8339 | L2064 | D2014-020 | 100 | 54 | N |  | 962 | RTC DD | Sandy Valley - Columbia Pass | Sandy Valley - Columbia Pass | [10 empty] | F
57 | Searchlight - West Channel | FSEA02B | TBD | TBD | TBD | 2020-11-02 | A | Design | TBD | Christine | TBD | CH2M Hill | TBD | 2019 | 0 | 5000000 | 2758.6088 | L2233 | D2019-012 | 90 | 38 | N | [15 empty] | A
58 | Sim Street, Marley Way to Warm Springs Rd | [8 empty] | Tim Piparo |  | In House | [5 empty] | L2500 | D2024-009 | 30 |  | N | [15 empty] | B
59 | Sloan Lane, Vegas Valley Dr to Ruby Creek Dr | R213AFT | 2020 |  | TBD | 2020-09-01 | E | Design |  | Christine | TBD | GCW, Inc. | RTC | 2019 |  | 7000000 | 2568.4205 | L2219 | D2018-024 | ADV | 21 | Y | [15 empty] | E,G
60 | Sloan Channel East Branch | MDD0001 | [7 empty] | Bryan/Joe |  | In House | [5 empty] | L2494 | D2024-004 | 100 |  | N | [15 empty] | B
61 | Spencer Street Storm Drain - Silverado Ranch Blvd to Serene Ave | MDD0001 | [7 empty] | Bryan/Jinxin |  | In House | [5 empty] | L2517 | D2024-017 | 0 | _ | N | [15 empty] | A
62 | Spring Mountain/Arville Signal (Phase 1) | N220713 | [7 empty] | GCW/ Rahel/Kaizad |  | Jacobs | [5 empty] | L2399 | D2022-23 | 30 | _ | N | [15 empty] | F
63 | Spring Mountain, Rainbow to Decatur (Phase 2) | N220713 | [7 empty] | GCW/ Rahel/Kaizad |  | Jacobs | [5 empty] | L2539 | D2024-031 | 30 | _ | N | [15 empty] | F
64 | Spring Mountain, Decatur to Aldebaran (Phase 3) | N220713 | [7 empty] | GCW/ Rahel/Kaizad |  | Jacobs | [5 empty] | L2540 | D2024-032 | 30 | _ | N | [15 empty] | F
65 | Starr Avenue, Las Vegas Boulevard to Bermuda Avenue | R245AFT | [7 empty] | Bryan Osborne |  | Kleinfelder | [5 empty] | L2312 | D2020-016 | 90 | 96 | Y | [15 empty] | A
66 | Sunrise Manor Planning - I-515 from Desert Inn to Mojave and I-515 at Sahara | BW22330 | [7 empty] | Kaizad Yazdani |  | WSP USA | [5 empty] | L2391 | D2022-018 | PEL Study (Hold) | 0 | N | [15 empty] | E
67 | Sunset Park - Duck Creek Wash to Eastern | FCLA14X | [7 empty] | GCW/ Rahel |  | CA Group | [5 empty] | L2461 | D2022-010 | 0 | _ | N | [15 empty] | G
68 | Sunset Road, Durango Drive to Decatur Boulevard | R240CFT | [7 empty] | Bryan/John McAvoy |  | _____ | [5 empty] | L2330 | D2021-015 | 60 | 55 | N | [15 empty] | F
69 | Thomas Edison Detention Basin | FLAU05A | [7 empty] | Rahel Shibeshi |  | CA Group | [5 empty] | L2504 | D2024-011 | 0 | 102 | N | [15 empty] | A
70 | Tompkins Avenue, Koval Ln to University Center Drive | S190107 | 2020 | TBD | TBD | 2020-09-01 | G | Design | TBD | Richard Robinson | TBD | GCW, Inc. | MTP Resort | 2020 | 0 | 8779000 | 4227.7662 | L2397 | D2020-010 | 60 | 89 | N |  | 983 | MTP Resort | Tompkins Avenue, Koval Ln to Paradise Ave | Tompkins, Koval to Paradise | [10 empty] | G
71 | Tropicana and University Center DDI | S160824 | [7 empty] | Kaizad Yazdani |  | CH2M Hill | [5 empty] | L2365 | D2016-16 | 60 | 15 | Y | [15 empty] | G
72 | Tropicana Avenue, Durango to Jones (Phase 1) | R006KFT | [7 empty] | GCW/ Rahel |  | CA Group | [5 empty] | L2332 | D2021-19 | ADV | 3 | Y | [15 empty] | A
73 | Tropicana, Jones to Valley View (Phase 2) | R006KFT | [7 empty] | GCW/ Rahel |  | CA Group | [5 empty] | L2541 | D2024-033 | 100 | 3 | Y | [15 empty] | A
74 | Tropicana Ave, Andover Dr to Wetlands Park Ln | R006LFT/ FCLA35B | [7 empty] | Richard Robinson |  | Jacobs | [5 empty] | L2493 | D2024-003 | 30 | 100 | N | [15 empty] | G
75 | Tropicana Detention Basin Ramp | MDD0001 | [7 empty] | Bryan/Shawn |  | In House | [5 empty] | L2499 | D2024-008 | 100 |  | N | [15 empty] | A
76 | Valley View Boulevard Storm Drain Project | B840225 | [7 empty] | Bryan/ Rahel Shibeshi |  | In House | [5 empty] | L2291 | D2020-011 | 100 | _ | N | [15 empty] | A
77 | Valley View Blvd, Windmill Ln to Mesa Verde Ln | B840212 | [7 empty] | Rahel |  | In House | [5 empty] | L2367 | D2021-027 | 100 | 86 | Y | [15 empty] | A
78 | Vegas Valley Drive, Lamb Blvd to Las Vegas Wash | R057DFT | [7 empty] | Ryan Dela Cruz |  | In House | [5 empty] | L2480 | D2021-023 | 90 | 52 | Y | [15 empty] | E
79 | Vegas Valley Drive, Las Vegas Wash to Los Feliz St | R057DFT | [7 empty] | Christine |  | WSP | [5 empty] | L2356 | D2021-023 | 60 | 52 | Y | [15 empty] | E
80 | Warm Springs Road, Decatur Boulevard to Dean Martin Drive | R046LFT | [7 empty] | Bryan/ Rahel/Jinxin |  | In House | [5 empty] | L2289 | D2020-008 | 90 | 5 | Y | [15 empty] | A